## Action Items
Item Group | Item | Comments | Owner | Current state | ETA | Status
Admin | Absence request forms and Reporting Absence Plan | move away from excel. MS Flows | NL | Silviya P workign on it. To test with one account | 2022-09-16
Admin | Reporting Skills Matrix | By client and tools. Revise current matrix. Create similar matrix for programs e.g VBA/VBS/Powershell/Python/Excel…. | All | basic advanced expert levels. Specify inlcusions in different levels ! 10 chapters | 2022-10-30 | to discuss internally. End of Sept
Admin | Action Log | Explore options to utilize ITSMC for internal usage | GT
Admin | Documentation | Working instructions. One Note/SharePoint. - Process documentation - process documentation owner/reviewer |  | AY to check issues when opening the files. Move to Sharepoint | End of Sept - standard approach
Admin | Documentation | IT setup - new comers. Process to request. Standard set of IT equipment/software/licenses/accesses/groups - prepare for IT and document process | NL | almost finalized. Hristo to ensure Martin K is aware
Admin | Documentation | New comer guide | AY | work with NL
Organization | Backup coverage | Each person to have at least 2 ppl capable to cover for him during absence. No exceptions for ppl logging during holiday.
Organization | New starters/internal moves | Standard trainings - corp onboarding/telephony |  | to check with Niki A. Aided by..
Organization | New clients setup | Prepare a set of reports as standard acrosss clients - BG projects |  |  | Q1 2023
Organization | Access DB migration |  |  |  | targeting EOY
Organization | Reporting unified ETL | Too many access DB/SQL/ etc. Python/Powershell.. |  |  | Q1 2023
Organization | "How to" repository | Organize "How to" handbook with examples/links
Organization | Useful files | Document system findings e.g. Outbound calls/Avaya specifics/Altitude/Salesforce…
Organization | Useful files | Repository with Samples of visualizations
Organization | Useful files | Repository with scripts related to data processing
Admin | Folder management | remove/archive redundant data/old clients. Everything except for Access DB/Source files to be moved to Sharepoint
Organization
Admin | Documentation | Process documentation Guidence all processes
Process | Remote machines utilization | Split workload between the machines and backup capabilities