## Action Log
Open Items
|  | R | A | G
| Open | 0 | 0 | 6
| Closed | 0 | 1 | 33
| Cancelled | 0 | 2 | 3 | [7 empty] | 2025-06-25
| Pending | 0 | 0 | 0
ID | Date Raised | Owner | Site | Campaign | Item Title | Comments | Action step with | Requestor | Target Completion date | Priority | RAG Status | Task Status
1 | 2024-01-15 | NR | Sofia | Medtronic | Power BI Dashboard | Create Medtronic Dashboard. Awaiting the DL from Sergey to grant access to it. | NR | Georgi Tsatsev | 2024-03-15 | 1 | G | Closed
2 | 2024-02-15 | NR | Sofia | Medtronic | CMSR | CMSR setup automation. On hold for now. Awaiting detais from Valentin. Account Manager has decided to take it over. | VA | Georgi Tsatsev |  | 3 | G | Cancelled
3 | 2024-03-01 | NR | Sofia | Medtronic | Icoach | iCoach setup was completed by ST. 100% Automated. Next step is to aligned with OPS if that is all they need. Nothing else needed from OPS during our call on 2024-05-29 | VA | Georgi Tsatsev | 2024-04-30 | 3 | G | Closed
4 | 2024-03-01 | NR | Sofia | Medtronic | Quality Data incorporation into PBI | Review the Form presented and had a call with Alex G. on specifics they want to review. Initial data added. Meeting with Alex and MDT team next week in the office so we can furter discuss and finalize the Quality. | NR | Alexandra Gorbunenko | 2024-03-31 | 2 | G | Closed
5 | 2024-03-01 | NR | Sofia | Medtronic | Telephony data incorporation into PBI | Data has been incorportated by MS. All good | NR | Georgi Tsatsev | 2024-03-15 | 1 | G | Closed
6 | 2024-03-01 | NR | Sofia | Medtronic | Telephony data mapping | Varna Teams mapping completed by Sergey. Once UK support has been shut down, remapping will be done for all other supported splits. Meeting on 04-04-2024 to start mapping correctly | SK | Georgi Tsatsev | 2024-04-08 | 1 | G | Closed
7 | 2024-03-01 | NR | Sofia | Medtronic | Forecast data incorporation into PBI | Forecast data incorporated in PBI by MS. Due to missing CT for all countries (except Sofia). Don't have it for all counties - Sergey will upload for Germany Today (15/03/2024). Forecast are being uploaded on 12/04/2024. Due to multiple Skills with one CT, working on proper distibution by 19/04/2024. | NR | Georgi Tsatsev | 2024-04-24 | 1 | G | Closed
8 | 2024-03-19 | NR | Sofia | Medtronic | CSAT data incorporation into PBI | NPS data to be added to PBI | NR | Sergey Kamenov | 2024-03-22 | 1 | G | Closed
9 | 2024-03-19 | NR | Sofia | Medtronic | Agent Level view in PBI | In progress, finilizing the views. Review with OPS when complete | NR | Sergey Kamenov | 2024-03-29 | 1 | G | Closed
10 | 2024-03-19 | NR | Sofia | Medtronic | Training compliance | Training compliance to be added in PBI. FE OPS are currently negotiating for one file to be sent on weekly basis (currently there are multiple files with different kind of data inside (missing columns and due dates). Once file is available, I'll start the implementation. I asked to be included in the conversation/comms so that I can support the team if I see something missing. Team does not have the unified report - still in discussion with Client (2024-05-31)). On hold due low interest from OPS and I was asked to leave for now | SK | Sergey Kamenov | TBD | 3 | A | Cancelled
11 | 2024-03-19 | NR | Sofia | Medtronic | WBR/MBR/QBR | Ops will sit down and prepare requirements of the report, then send template my way. No response from Management as of 02-04-2024. Reminder during one on one with Valio was done on 01-04-2024. Already set up the QBR template. WBR and MBR templates provided by OPS. Working on them. | SK/VA | Sergey Kamenov | 2024-06-07 | 3 | G | Closed
12 | 2024-03-19 | NR | Sofia | Medtronic | Quality PO integration into Quality data | No access to the client tool. Contacted the ppl (02-04-2024) with access to arange a meeting to understand what data is needed and how to link it to our people. Awaiting feedback from TLs in order to understand the neededs and data behind it. No action since April 2024. As it is not a topic to incorporate as they receive daily mails on this and they manage as is, canceling the request. | SK | Sergey Kamenov | 2024-04-12 | 2 | A | Cancelled
13 | 2024-05-27 | NR | Sofia | Medtronic | Shrinkage & Adherence | IEX Data incorporation in our Server with one week data for first touch PBI Dash. Contacted WFM and OPS for additional clarifications on KPI definition - Awaiting Feedback (2024-06-27). IEX Data mapping not possible due to incorrect IEX_Agent_ID or HR_ID not reflect Boost ID. Send a mail to OPS to talk to WFM and either correct that or will not include Agent details (2024-07-04). First steps in PBI created. With more feedback will complete the dashboard | NR | Sergey Kamenov | 2024-08-29 | 1 | A | Closed
14 | 2024-06-03 | NR | Sofia | Medtronic | Intra-Day PBI Dashboard | Escalation from Client for Intra-Day report. PBI Dashboard has been created. Mock up meeting with FE OPS and AMs on 07/06/2024 to review and do any last touches. If no issues - expected release of the report is 10/07/2024. | OPS | Mohamed Albadersarsri | 2024-06-10 | 1 | G | Closed
15 | 2024-10-22 | NR | Multiple | Medtronic | SFTP Data transfer | Transfer Call Data on daily basis to MDT SFTP. File created and approved by client. Currently in testing stage. Once testing complete I will set up the automation of the transfer and create a guide. Waiting on IT to whiteflag the IP for production SFTP and will be done | Medtronic IT Team | Medtronic | 2024-11-30 | 1 | G | Closed
16 | 2024-06-18 | NR | Sofia | Medtronic | Measure ASA on agent level | Awaiting feedback from OPS - as ASA cannot be measured on agent level - sujested to add Answer Ring Time (2024-06-21). Agreed to use Answer Ring Time | NR | Sergey Kamenov | 2024-06-28 | 2 | G | Closed
17 | 2024-06-18 | NR | Sofia | Medtronic | Can we format agent level data in more readable format? (AUX usage) | In Time Format | NR | Sergey Kamenov | 2024-06-28 | 2 | G | Closed
18 | 2024-06-18 | NR | Sofia | Medtronic | Usage Report for MDT dashboard | Sergo needed usage report for MDT dasboard | NR | Sergey Kamenov | 2024-06-21 | 3 | G | Closed
19 | 2024-06-18 | NR | Sofia | Medtronic | Repeat calls add to PBI | Can we review SAP data and our possibilities to analyzed/link it to agents? To get only repeat caller per day for Germany. Ready to build - awaiting final configurations from Sergey, what they want to see as no way to catch ANI as they go to generic number. Currently on hold as process is still no clear on requirements from client. Cancelled - client will get access directly without any assistance on Reporting side. Sergo confirmed during a call | SK | Sergey Kamenov | 2024-10-30 | 2 | G | Cancelled
20 | 2024-06-18 | NR | Sofia | Medtronic | Login Logout add to PBI | Piotr requested the Login / Logout report only with actual data in it to be created so that the TLs can see what their Agents are doing | NR | Piotr T. | 2024-08-02 | 1 | G | Closed
21 | 2024-08-24 | NR | Multiple | Lexmark | Skill Remapping | Manual review and remapping of all ~800 skills for client. List of skills created. Review with managers of all sites. Manila site left to finish and send list to AM & CI. | NR | Olga Gagauz <Olga.Gagauz@foundever.com> | 2024-11-01 | 1 | G | Closed
22 | 2024-09-30 | NR | Multiple | Lexmark | Support for EMEA Genesys implementation for Rafael De La Chica <rafael.delachica@foundever.com> | Provide Skill information and mapping as well as raw data | MJ | Mary Jane Suratos <MaryJane.Suratos@foundever.com> | 2024-11-01 | 1 | G | Closed
23 | 2024-10-01 | NR | Sofia | Medtronic | iCoach | Valentin requested iCoach for MDT. I developed a view in MDT DB, however iCoach was not set up as template provided. MDT OPS in discussion with AM to determine KPIs and LOB. 2025-02-13 New KPIs and logic provided by Bozhidar Georgiev (BPI). Implementation in progress. 2025-02-24 Implementation completion 202-02-25 - schedule for first test upload in iCoach. DELAY with set up from iCoach side. Bozhidar Georgiev will let us know when import and creation in system are complete. Put on HOLD for now. ## 2025-03-21 - task completed | BG | Valentin Antonov | 2025-03-31 | 2 | G | Closed
24 | 2024-10-10 | NR | Multiple | Lexmark | Lexmark CSAT IVR automation process | I was able to grant Vitor access to our Server, so he can use the same user and password as Abbott user “csat_batch” that gives him access to DB “CS_Lexmark” schema “stg”. Table “survey_CTI_temp” | VS | Nikolay Raykov | TBD | 3 | G | Cancelled
25 | 2024-10-22 | NR | Multiple | Medtronic | Quality PO integration into Quality data | No access to the client tool. Maria Topalova sent first reprt samples for review by Reporting team.MCM And Roster have been implemented. PO data import in progress | MT | Maria Topalova | 2024-12-12 | 2 | G | Closed
26 | 2024-11-29 | NR | Multiple | Medtronic | Call Recording data implementation in PBI | Sergo asked to get the call recordings in PBI Dashboard. He is wokring with Stuart to get specific VDNs for recording. Once done I'll start developing. Decided to go with COR BO report. Closing request | SK | Sergey Kamenov | TBD | 2 | G | Closed
27 | 2024-11-26 | NR | Multiple | Lexmark | OLD Monthly reporting tool - excel | Olga asked me to send old Reporting template and after review I saw a lot if info missing as well as calls. I'll need to redo the whole template and create a clear instruction that will not make issues. For that I sent mail for alignment and meeting to discuss new points | OG | Olga Gagauz <Olga.Gagauz@foundever.com> | 2024-12-31 | 1 | G | Closed
28 | 2024-12-13 | NR | Multiple | Lexmark | NICE Quality | Implementation of NICE in PBI. ON Hold till Genesys implementation is done. | MJS | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 1 | G | Open
29 | 2025-01-28 | NR | Multiple | Lexmark | Absenteeism Report | Create PBI | NR | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 2 | G | Open
30 | 2025-01-28 | NR | Multiple | Lexmark | Attrition Report | Create PBI | NR | Olga Gagauz <Olga.Gagauz@foundever.com> | 2025-03-31 | 2 | G | Closed
31 | 2025-01-28 | NR | Multiple | Lexmark | Forecast data | Forecast data incorporation into PBI | NR | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 3 | G | Open
32 | 2025-02-26 | NR | Sofia | Lexmark | Genesys - Telephony | Genesys - Telephony implementation | NR | Olga Gagauz <Olga.Gagauz@foundever.com> | 2025-03-31 | 1 | G | Closed
33 | 2025-02-26 | NR | Sofia | Lexmark | Genesys - IVR CSAT | Genesys - IVR CSAT | NR | Olga Gagauz <Olga.Gagauz@foundever.com> | 2025-03-31 | 1 | G | Closed
34 | 2025-03-06 | NR | Sofia | Lexmark | PBI | PBI combine data with Avaya and Genesys | NR | Olga Gagauz <Olga.Gagauz@foundever.com> | 2025-03-28 | 1 | G | Closed
35 | 2025-03-18 | NR | Rabat | Lexmark | Genesys - Telephony | Genesys - Telephony implementation | NR | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 2 | G | Closed
36 | 2025-03-18 | NR | Rabat | Lexmark | Genesys - IVR CSAT | Genesys - IVR CSAT | NR | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 2 | G | Open
37 | 2025-02-26 | NR | Sofia | Medtronic | Bonus Scheme | Create Bonus Scheme based on requirement in mail: Medtronic Dev Request | NR | Sergey Kamenov <Sergey.Kamenov@foundever.com> | 2025-04-30 | 2 | G | Closed
38 | 2025-03-06 | NR | Multiple | Multiple | Agent Tenure - All sites | Add Agent Tenure to all BG clients | NR | Bozhidar Georgiev <Bozhidar.Georgiev@foundever.com> | 2025-03-26 | 1 | G | Closed
39 | 2025-03-06 | NR | Multiple | Medtronic | CMSR | CMSR setup automation. | NR | Sergey Kamenov <Sergey.Kamenov@foundever.com> | 2025-03-31 | 1 | G | Closed
40 | 2025-03-14 | NR | Sofia | Lexmark | iAnalyze | Takeover of iAnalyze toll from Alexandra to me. Set up of Dataverse in Power APPS. Currently looking for a way to take over without loss of data and tool functions. | NR | Olga Gagauz <Olga.Gagauz@foundever.com> |  | 3 | G | Open
41 | 2025-02-26 | NR | Egypt | Medtronic | Medtronic Cairo - PBI | Medtronic Cairo - Data integrestion. Waiting on Cairo data. | VA | Valentin Antonov |  | 3 | G | Closed
42 |  |  |  | Medtronic | Medtronic Cairo | Fix the issue where cairo agent names are not appearing in WFM IEX PBI report | IT | Hasnaa Zaghloul | 2025-06-24 | 3 | G | Closed
43 |  |  |  | Medtronic | PBI | Create PBI report on ANI Level only with the repetitive calls | IT | Sergey Kamenov | 2025-06-25 | 1 | G | Closed
44 |  |  |  | Medtronic | Ad-hoc ANI report | Create pivot table in excel with ANI level data only for Poland | IT | Sergey Kamenov | 2025-06-25 | 1 | G | Closed
45 |  |  |  | Medtronic | PO Report deep-dive | Add Activity partner information in the PO agent level data | VP | Sergey Kamenov | 2025-06-30 | 2 | G | Open
ACTION LOG

## Report Creation (hidden)
Open Items
|  | R | A | G
| Open | 0 | 0 | 0
| Closed | 0 | 0 | 3
| Cancelled | 0 | 0 | 0 | [7 empty] | 2025-06-25
| Pending | 0 | 0 | 0
ID | Date Raised | Owner | Site | Campaign | Item Title | Comments | Action step with | Requestor | Target Completion date | Priority | RAG Status | Task Status
1 | 2023-04-12 | NR | Belgrade | DE | Billable Hours | Weekly report to check for data discrepancies with billing data. Fully automated | NR | Herbert, Andre <Andre.Herbert@tui.de> | 2023-04-22 | 3 | G | Closed
2 | 2023-04-11 | NR | Larnaca | NOR | Weekly Performance Report | New report to represent agents data and weekly results | NR | Ricardo Garcia <Ricardo.Garcia2@foundever.com> | 2023-04-22 | 1 | G | Closed
3 | 2023-04-20 | NR | Varna | UK | CSAT Report | Create a new dashboard specifically for CSAT | NR | Aslihan Hasan <Aslihan.Hasan@foundever.com> ; Estel Dimova <Estel.Dimova@foundever.com> | 2023-05-05 | 1 | G | Closed
New Reports

## Monthly (hidden)
Open Items
|  | R | A | G
| Open | 0 | 0 | 0
| Closed | 0 | 0 | 5
| Cancelled | 0 | 0 | 0 | [7 empty] | 2025-06-25
| Pending | 0 | 0 | 0
ID | Date Raised | Owner | Site | Campaign | Item Title | Comments | Action step with | Requestor | Target Completion date | Priority | RAG Status | Task Status
1 |  | SP | Plymouth | JL | Sitel Plymouth Site Tracker 2022 | Done for July | SP, NR | Rowan Marshall | 2022-06-28 | 3 | G | Closed
2 |  | SP | Exeter |  | SIOX Forecast | Done for July | SP, NR |  | 2022-06-28 | 3 | G | Closed
3 |  | SP | Exeter | JL | Sitel Exeter Site Tracker 2022 | Done for July | SP, NR | Regular report | 2022-07-22 | 3 | G | Closed
4 |  | SP | Exeter |  | SIOX Forecast | Done in August | SP, NR |  | 2022-08-04 | 3 | G | Closed
5 |  | SP | Exeter |  | SIOX Forecast | Done in September | SP, NR |  | 2022-09-25 | 3 | G | Closed
MONTHLY LOG

## System (hidden)
Status | Priority | Comment | RAG | Comment
Open | 1 | High | R | Overdue
In Queue | 2 | Medium | A | At Risk
Cancelled | 3 | Low | G | On Target
Closed
Pending